## DATA
Project_ID | Project_Name | Client | Region | Start_Date | End_Date | Contract_Value_EUR | Actual_Cost_EUR | Forecast_Cost_EUR | Invoiced_EUR | Cash_In_EUR | Committed_Cost_EUR | Project_Manager | Status
P001 | Steel Structure Assembly – Plant A | Client A | Poland | 2025-01-10 | 2025-09-30 | 1200000 | 800000 | 1100000 | 900000 | 750000 | 200000 | Kowalski | Active
P002 | Pipeline Installation – Refinery | Client B | Germany | 2025-02-01 | 2025-11-30 | 2000000 | 1500000 | 2100000 | 1600000 | 1400000 | 300000 | Nowak | Delayed
P003 | Tank Construction – Chemical Site | Client C | Czech Republic | 2025-03-15 | 2025-10-15 | 1500000 | 1000000 | 1400000 | 1200000 | 1100000 | 250000 | Zieliński | Active
P004 | Production Hall Expansion | Client D | Poland | 2025-01-20 | 2025-08-30 | 1800000 | 1700000 | 1900000 | 1750000 | 1600000 | 150000 | Wiśniewski | Delayed
P005 | Electrical Systems Upgrade | Client E | Germany | 2025-04-01 | 2025-12-31 | 900000 | 500000 | 800000 | 600000 | 550000 | 100000 | Kamiński | Active
P006 | Wastewater Treatment модернизация | Client F | Poland | 2025-02-10 | 2025-09-10 | 1300000 | 900000 | 1200000 | 950000 | 850000 | 200000 | Lewandowski | Active
P007 | Warehouse Automation Project | Client G | Czech Republic | 2025-03-01 | 2025-11-01 | 2200000 | 1600000 | 2000000 | 1700000 | 1500000 | 350000 | Dąbrowski | Active
P008 | Industrial Piping System | Client H | Poland | 2025-05-01 | 2025-12-15 | 1100000 | 600000 | 1000000 | 700000 | 650000 | 180000 | Kaczmarek | Active
P009 | HVAC Installation | Client I | Germany | 2025-01-15 | 2025-07-30 | 800000 | 750000 | 900000 | 780000 | 700000 | 120000 | Mazur | Delayed
P010 | Energy Efficiency Upgrade | Client J | Poland | 2025-02-20 | 2025-10-20 | 1400000 | 900000 | 1300000 | 1000000 | 950000 | 220000 | Krawczyk | Active
P011 | Steel Tank Renovation | Client K | Czech Republic | 2025-03-05 | 2025-09-25 | 950000 | 700000 | 900000 | 800000 | 750000 | 100000 | Piotrowski | Completed
P012 | Process Line Modernization | Client L | Germany | 2025-04-10 | 2025-12-10 | 2100000 | 1700000 | 2200000 | 1800000 | 1600000 | 300000 | Grabowski | Delayed
P013 | Assembly Line Extension | Client M | Poland | 2025-05-15 | 2025-11-15 | 1250000 | 800000 | 1200000 | 900000 | 850000 | 200000 | Zając | Active
P014 | Boiler System Installation | Client N | Germany | 2025-01-25 | 2025-08-25 | 1600000 | 1200000 | 1500000 | 1300000 | 1200000 | 250000 | Król | Completed
P015 | Chemical Plant Upgrade | Client O | Czech Republic | 2025-02-28 | 2025-10-30 | 2300000 | 1800000 | 2400000 | 1900000 | 1700000 | 400000 | Wieczorek | Delayed